## Defects
SL No | Description | Detected Sprint | Assigned to | Type of Defect | Action Teken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Inconsistent labels found in training dataset | Sprint 1 | Samiksha | Data Defect | Cleaned dataset and standardized labels | 2025-11-29 | Closed | Improved data quality
2 | Text preprocessing removed important keywords | Sprint 1 | Samiksha | Functional Defect | Updated stop-word list and preprocessing rules | 2025-12-04 | Closed | Accuracy improved
3 | Low accuracy in ticket classification model | Sprint 1 | Samiksha | Performance Defect | Tuned TF-IDF parameters and retrained model | 2025-12-07 | Closed | Model performance stabilized
4 | NER failed to extract certain entities | Sprint 1 | Samiksha | Functional Defect | Improved NER patterns and training data | 2025-12-12 | Closed | Entity extraction improved
5 | Priority prediction incorrect for urgent tickets | Sprint 1 | Samiksha | Logic Defect | Added rule-based priority override | 2025-12-13 | Closed | Correct priority assigned
6 | 6 | Sprint 2 | Samiksha | Functional Defect | Fixed backend status update workflow | 2025-12-28 | Closed | Status now updates correctly
7 | Ticket status update not reflecting correctly | Sprint 3 | Samiksha | Performance Defect | Optimized Streamlit state handling | 2026-01-08 | Closed | UI responsiveness improved
8 | Delay in UI response during ticket submission | Sprint 3 | Samiksha | Integration Defect | Performed integration testing and bug fixes | 2026-01-15 | Closed | End-to-end flow stable
9 | UI and backend integration issues | Sprint 3 | Samiksha | System Defect | Fixed bugs and retested system | 2026-01-16 | Closed | No critical issues remaining
10 | Minor bugs found during system testing | Sprint 3 | Samiksha | Regression Defect | Resolved issues and validated again | 2026-01-18 | Closed | Project finalized
11 | Edge case failures identified in regression testing